## JIT Purchase Tracker
Voron 2.4 – JIT Purchase Tracker (Ordered by Assembly Step)
Sorted by the assembly step that first needs each part ¦ ⚡ Yellow rows = Buy ALL at first step needed (fasteners, bearings, etc.) — same logic as pre-buying all your screws ¦ Generated from Voron Configurator BOM
When to Buy (Assembly Step) | BOM Category | Description | Qty | Buy All Now? | Purchase Notes | Est Unit Price (USD) | Total Est Cost | Status | Purchased From | Order # | Date Ordered | Date Received | ✓
▶ 1 – FRAME — Buy these parts before this assembly step
1 – Frame | Fasteners | M5x40 SHCS | 22 | ⚡ Buy All Now | Frame extrusion assembly |  |  | Research |  |  |  |  | ☐
1 – Frame | Fasteners | M5x30 BHCS | 22 | ⚡ Buy All Now | Frame extrusion assembly |  |  | Research |  |  |  |  | ☐
1 – Frame | Fasteners | M5x16 BHCS | 35 | ⚡ Buy All Now | Frame/panel clips |  |  | Research |  |  |  |  | ☐
1 – Frame | Fasteners | M5x10 BHCS | 35 | ⚡ Buy All Now | Frame extrusion assembly |  |  | Research |  |  |  |  | ☐
1 – Frame | Fasteners | M5 Hexnut | 16 | ⚡ Buy All Now | Frame assembly |  |  | Research |  |  |  |  | ☐
1 – Frame | Fasteners | M5 Post-install T-nut | 68 | ⚡ Buy All Now | Used throughout entire build |  |  | Research |  |  |  |  | ☐
1 – Frame | Fasteners | M3 Post-install T-nut | 96 | ⚡ Buy All Now | Used throughout entire build |  |  | Research |  |  |  |  | ☐
1 – Frame | Fasteners | M3 Hammer Head T-nuts | 60 | ⚡ Buy All Now | Used throughout entire build |  |  | Research |  |  |  |  | ☐
1 – Frame | Fasteners | M3 Threaded Insert (M3x5x4) | 110 | ⚡ Buy All Now | Install in all printed parts before assembly begins |  |  | Research |  |  |  |  | ☐
1 – Frame | Vibration Management | Rubber Foot (1.5x.75", 38x19mm) | 4 | Buy when needed | Attach to bottom frame during frame assembly |  |  | Research |  |  |  |  | ☐
1 – Frame | Frame | OpenBuilds Billet Angle Corner Connector (2020) | 4 | Buy when needed | Frame corner braces |  |  | Research |  |  |  |  | ☐
1 – Frame | Frame | Misumi HFSB5-2020-290 | 1 | Buy when needed | Frame extrusion |  |  | Research |  |  |  |  | ☐
1 – Frame | Frame | Misumi HFSB5-2020-380 | 1 | Buy when needed | Frame extrusion |  |  | Research |  |  |  |  | ☐
1 – Frame | Frame | Misumi HFSB5-2020-400 | 2 | Buy when needed | Frame extrusion |  |  | Research |  |  |  |  | ☐
1 – Frame | Frame | Misumi HFSB5-2020-420-TPW | 10 | Buy when needed | Frame extrusion |  |  | Research |  |  |  |  | ☐
1 – Frame | Frame | Misumi HFSB5-2020-480-LCP-RCP | 4 | Buy when needed | Frame extrusion |  |  | Research |  |  |  |  | ☐
1 – Frame | Misc | Loctite Blue Threadlocker Stick | 1 | ⚡ Buy All Now | Use throughout — buy at start |  |  | Research |  |  |  |  | ☐
▶ 2 – Z DRIVE ASSEMBLY — Buy these parts before this assembly step
2 – Z Drive Assembly | Fasteners | M3x40 SHCS | 30 | ⚡ Buy All Now | Z motor mounts — used throughout |  |  | Research |  |  |  |  | ☐
2 – Z Drive Assembly | Fasteners | M3x30 SHCS | 25 | ⚡ Buy All Now | Z drive — used throughout |  |  | Research |  |  |  |  | ☐
2 – Z Drive Assembly | Fasteners | M3x20 SHCS | 22 | ⚡ Buy All Now | Z drive — used throughout |  |  | Research |  |  |  |  | ☐
2 – Z Drive Assembly | Fasteners | M3x16 SHCS | 20 | ⚡ Buy All Now | Z drive — used throughout |  |  | Research |  |  |  |  | ☐
2 – Z Drive Assembly | Fasteners | M3x8 SHCS | 180 | ⚡ Buy All Now | Most common screw — buy all upfront |  |  | Research |  |  |  |  | ☐
2 – Z Drive Assembly | Fasteners | M3 Hexnut | 6 | ⚡ Buy All Now | Z endstop & throughout |  |  | Research |  |  |  |  | ☐
2 – Z Drive Assembly | Fasteners | M3 Washer | 4 | ⚡ Buy All Now | Z drive assembly |  |  | Research |  |  |  |  | ☐
2 – Z Drive Assembly | Motion | GT2 80T Pulley (5mm ID 6mm W) | 4 | Buy when needed | Z drive belt loops × 4 |  |  | Research |  |  |  |  | ☐
2 – Z Drive Assembly | Motion | F695 Bearing | 20 | ⚡ Buy All Now | Z & XY idler bearings — buy all, used throughout |  |  | Research |  |  |  |  | ☐
2 – Z Drive Assembly | Motion | 625 Bearing | 12 | ⚡ Buy All Now | Z idler bearings — buy all |  |  | Research |  |  |  |  | ☐
2 – Z Drive Assembly | Motion | GT2 Belt Loop (6mm W) - 188mm | 4 | Buy when needed | Z drive belt loops × 4 |  |  | Research |  |  |  |  | ☐
2 – Z Drive Assembly | Motion | Linear Rail MGN9H 350mm | 6 | Buy when needed | Z axis rails × 6 — install before Z drives go in |  |  | Research |  |  |  |  | ☐
2 – Z Drive Assembly | Electronics | NEMA17 Motor 17HS19-2004S | 6 | ⚡ Buy All Now | Z motors × 4 + A/B motors × 2 — buy all 6 |  |  | Research |  |  |  |  | ☐
2 – Z Drive Assembly | Misc | Mobil EP1/2 Grease | 1 | ⚡ Buy All Now | Linear rail lubrication — buy at start |  |  | Research |  |  |  |  | ☐
▶ 3 – AB DRIVE MODULES — Buy these parts before this assembly step
3 – AB Drive Modules | Fasteners | M5 1mm Shim | 42 | ⚡ Buy All Now | AB drives & idlers |  |  | Research |  |  |  |  | ☐
3 – AB Drive Modules | Fasteners | M3x25 SHCS | 6 | ⚡ Buy All Now | AB drive frames |  |  | Research |  |  |  |  | ☐
3 – AB Drive Modules | Fasteners | M3x12 SHCS | 41 | ⚡ Buy All Now | AB drives — used throughout |  |  | Research |  |  |  |  | ☐
3 – AB Drive Modules | Motion | GT2 20T Pulley (5mm ID 6mm W) | 3 | Buy when needed | AB drive pulleys |  |  | Research |  |  |  |  | ☐
3 – AB Drive Modules | Motion | GT2 20T Pulley (5mm ID 9mm W) | 4 | Buy when needed | AB drive pulleys (9mm) |  |  | Research |  |  |  |  | ☐
3 – AB Drive Modules | Motion | GT2 16T Pulley (5mm ID 6mm W) | 4 | Buy when needed | AB motor drive pulleys |  |  | Research |  |  |  |  | ☐
3 – AB Drive Modules | Motion | GT2 20T Toothed Idler (5mm ID 6mm W) | 2 | Buy when needed | AB/XY idlers |  |  | Research |  |  |  |  | ☐
3 – AB Drive Modules | Motion | GT2 20T Toothed Idler (5mm ID 9mm W) | 4 | Buy when needed | AB/XY idlers (9mm) |  |  | Research |  |  |  |  | ☐
3 – AB Drive Modules | Motion | Ø5x60mm Shaft, D Cut | 4 | Buy when needed | AB drive shafts × 4 |  |  | Research |  |  |  |  | ☐
3 – AB Drive Modules | Motion | Ø5x35mm Shaft (trim to size) | 1 | Buy when needed | Extruder drive shaft |  |  | Research |  |  |  |  | ☐
3 – AB Drive Modules | Motion | GT2 Open Belt LL-2GT-6 (6mm wide) - 1800mm | 2 | Buy when needed | XY gantry belts × 2 |  |  | Research |  |  |  |  | ☐
▶ 4 – GANTRY / XY JOINTS — Buy these parts before this assembly step
4 – Gantry / XY Joints | Fasteners | M3x10 FHCS | 4 | ⚡ Buy All Now | XY joints flush screws |  |  | Research |  |  |  |  | ☐
4 – Gantry / XY Joints | Fasteners | M3x6 FHCS | 8 | ⚡ Buy All Now | XY joints flush screws |  |  | Research |  |  |  |  | ☐
4 – Gantry / XY Joints | Motion | Linear Rail MGN12H 350mm | 1 | Buy when needed | X axis rail × 1 |  |  | Research |  |  |  |  | ☐
4 – Gantry / XY Joints | Electronics | Omron D2F-01L Micro Switch | 3 | Buy when needed | XY & Z endstop microswitches |  |  | Research |  |  |  |  | ☐
▶ 5 – TOOLHEAD — Buy these parts before this assembly step
5 – Toolhead | Motion | BMG Extruder Components Kit | 1 | Buy when needed | CW2/extruder components |  |  | Research |  |  |  |  | ☐
5 – Toolhead | Electronics | Inductive Probe (See sourcing guide) | 1 | Buy when needed | Z probe on toolhead |  |  | Research |  |  |  |  | ☐
5 – Toolhead | Electronics | Hotend Kit (24V) | 1 | Buy when needed | Hotend |  |  | Research |  |  |  |  | ☐
5 – Toolhead | Electronics | 50x50x15 Centrifugal Fan (24V) | 1 | Buy when needed | Part cooling blower fan |  |  | Research |  |  |  |  | ☐
5 – Toolhead | Electronics | 40x40x10 Axial Fan (24V) | 1 | Buy when needed | Hotend heatsink fan |  |  | Research |  |  |  |  | ☐
5 – Toolhead | Electronics | NEMA14 Motor 36STH20-1004AHG | 1 | Buy when needed | Extruder motor |  |  | Research |  |  |  |  | ☐
5 – Toolhead | Misc | 4mm Threaded Bowden Coupler | 1 | Buy when needed | Hotend PTFE coupler |  |  | Research |  |  |  |  | ☐
5 – Toolhead | Misc | Ø6x3mm Neodimium Magnet | 8 | ⚡ Buy All Now | Probe & toolhead magnets — buy all |  |  | Research |  |  |  |  | ☐
5 – Toolhead | Misc | PTFE Tube (4mm OD 3mm ID) - 1000mm | 1 | Buy when needed | Bowden path |  |  | Research |  |  |  |  | ☐
5 – Toolhead | Misc | PTFE Tube (4mm OD 2mm ID) - 300mm | 1 | Buy when needed | Hotend PTFE liner |  |  | Research |  |  |  |  | ☐
▶ 6 – BELTING Z DRIVE — Buy these parts before this assembly step
6 – Belting Z Drive | Motion | GT2 Open Belt LL-2GT-9 (9mm wide) - 1100mm | 4 | Buy when needed | Z open belt × 4 |  |  | Research |  |  |  |  | ☐
▶ 7 – LCD MODULE — Buy these parts before this assembly step
7 – LCD Module | Electronics | Mini 12864 Display | 1 | Buy when needed | LCD display |  |  | Research |  |  |  |  | ☐
▶ 8 – SKIRTS — Buy these parts before this assembly step
8 – Skirts | Fasteners | M3x6 BHCS | 11 | ⚡ Buy All Now | Skirt assembly |  |  | Research |  |  |  |  | ☐
8 – Skirts | Electronics | 60x60x20 Fan (24V) | 3 | Buy when needed | Skirt exhaust fans × 3 |  |  | Research |  |  |  |  | ☐
▶ 9 – PANELS — Buy these parts before this assembly step
9 – Panels | Misc | Single Sided Foam Tape 1mm Thick (5m) | 1 | Buy when needed | Panel sealing |  |  | Research |  |  |  |  | ☐
9 – Panels | Misc | Single Sided Foam Tape 3mm Thick (5m) | 1 | Buy when needed | Panel sealing |  |  | Research |  |  |  |  | ☐
9 – Panels | Panels | Coroplast Sheet - 419x419x4 mm | 2 | Buy when needed | Side/back panels |  |  | Research |  |  |  |  | ☐
9 – Panels | Panels | Coroplast Sheet - 433x453x4 mm | 1 | Buy when needed | Bottom panel |  |  | Research |  |  |  |  | ☐
9 – Panels | Panels | Acrylic Sheet Clear - 216.5x453x3 mm | 2 | Buy when needed | Front door panels × 2 |  |  | Research |  |  |  |  | ☐
9 – Panels | Panels | Acrylic Sheet Clear - 433x453x3 mm | 2 | Buy when needed | Side panels × 2 |  |  | Research |  |  |  |  | ☐
9 – Panels | Panels | Acrylic Sheet Clear - 433x433x3 mm | 1 | Buy when needed | Top panel |  |  | Research |  |  |  |  | ☐
▶ 11 – EXHAUST FILTER — Buy these parts before this assembly step
11 – Exhaust Filter | Misc | Fume Extractor Carbon Filter Element | 1 | Buy when needed | Exhaust filter carbon |  |  | Research |  |  |  |  | ☐
▶ 12 – ELECTRONICS — Buy these parts before this assembly step
12 – Electronics | Fasteners | M3x50 SHCS | 2 | ⚡ Buy All Now | Electronics bay |  |  | Research |  |  |  |  | ☐
12 – Electronics | Fasteners | M2x10 Self-tapping Screw | 18 | ⚡ Buy All Now | Electronics/fan mounting |  |  | Research |  |  |  |  | ☐
12 – Electronics | Electronics | ZF Rocker Switch DPST 16A ON-OFF | 1 | Buy when needed | Power switch |  |  | Research |  |  |  |  | ☐
12 – Electronics | Electronics | TycoElectronics 10EGG1-1 Filtered Power Inlet (NA/UK) | 1 | Buy when needed | Mains inlet (NA/UK) |  |  | Research |  |  |  |  | ☐
12 – Electronics | Electronics | TycoElectronics 10EGG1-2 Filtered Power Inlet (EU) | 1 | Buy when needed | Mains inlet (EU) — pick one |  |  | Research |  |  |  |  | ☐
12 – Electronics | Electronics | Medium Blow Fuse 5x20mm 4A (220V mains) | 2 | ⚡ Buy All Now | Spare fuses — buy both variants |  |  | Research |  |  |  |  | ☐
12 – Electronics | Electronics | Medium Blow Fuse 5x20mm 8A (120v mains) | 1 | ⚡ Buy All Now | Spare fuses — buy both variants |  |  | Research |  |  |  |  | ☐
12 – Electronics | Electronics | Keystone CAT6 Insert (Optional) | 1 | Buy when needed | Optional network port in skirt |  |  | Research |  |  |  |  | ☐
12 – Electronics | Electronics | Controller with 7+ Stepper outputs | 1 | Buy when needed | Main MCU (e.g. BTT Octopus) |  |  | Research |  |  |  |  | ☐
12 – Electronics | Electronics | TMC2209 Stepper Motor Driver | 7 | ⚡ Buy All Now | Motor drivers — buy all 7 |  |  | Research |  |  |  |  | ☐
12 – Electronics | Electronics | USB Cable for selected controller | 1 | Buy when needed | MCU to RPi USB |  |  | Research |  |  |  |  | ☐
12 – Electronics | Electronics | RaspberryPi 3B+ or better | 1 | Buy when needed | Klipper host SBC |  |  | Research |  |  |  |  | ☐
12 – Electronics | Electronics | Mean Well LRS-200-24 PSU | 1 | Buy when needed | Main 24V PSU |  |  | Research |  |  |  |  | ☐
12 – Electronics | Electronics | Mean Well RS-25-5 PSU | 1 | Buy when needed | 5V RPi PSU |  |  | Research |  |  |  |  | ☐
12 – Electronics | Electronics | Omron G3A-210B-DC5 SSR | 1 | Buy when needed | Bed SSR |  |  | Research |  |  |  |  | ☐
12 – Electronics | Electronics | DIN Rail Mount Bracket for G3A SSR | 1 | Buy when needed | SSR DIN bracket |  |  | Research |  |  |  |  | ☐
12 – Electronics | Electronics | BAT85 Diode | 1 | Buy when needed | Probe signal conditioning |  |  | Research |  |  |  |  | ☐
12 – Electronics | Electronics | C13 Power Cord | 1 | Buy when needed | Mains power cord |  |  | Research |  |  |  |  | ☐
12 – Electronics | Frame | DIN 3 Rails (35mm W) - 415mm | 2 | Buy when needed | Electronics DIN rail |  |  | Research |  |  |  |  | ☐
12 – Electronics | Cables | Nylon Cable Ties, Small (.07-.10", 1.8-2.7mm wide) | 42 | ⚡ Buy All Now | Buy all — used throughout wiring |  |  | Research |  |  |  |  | ☐
12 – Electronics | Cables | 18AWG Wire (10ft/3m total) | 1 | Buy when needed | Mains/bed power wiring |  |  | Research |  |  |  |  | ☐
12 – Electronics | Cables | 20AWG High-flex Wire (10ft/3m total) | 1 | Buy when needed | Motor & heated bed wiring |  |  | Research |  |  |  |  | ☐
12 – Electronics | Cables | 22-24AWG High-flex Wire (min 19 strand)(250ft/76m total) | 1 | Buy when needed | Signal wiring throughout |  |  | Research |  |  |  |  | ☐
12 – Electronics | Cables | Female Spade Crimp Terminal (18-22AWG, .250", 6.35mm) | 7 | ⚡ Buy All Now | Crimp terminals — buy all |  |  | Research |  |  |  |  | ☐
12 – Electronics | Cables | Fork Spade Crimp Terminal (18-22AWG, #10) | 5 | ⚡ Buy All Now | Crimp terminals — buy all |  |  | Research |  |  |  |  | ☐
12 – Electronics | Cables | Ring Crimp Terminal (16-22AWG, #6) | 1 | ⚡ Buy All Now | Crimp terminals — buy all |  |  | Research |  |  |  |  | ☐
12 – Electronics | Cables | JST XH Connector, 3 Position Male/Female Pair plus Pins | 1 | ⚡ Buy All Now | Connectors — buy all |  |  | Research |  |  |  |  | ☐
12 – Electronics | Cables | Connector kit matching your controller choice (usually JST-XH) | 1 | Buy when needed | MCU-specific connector kit |  |  | Research |  |  |  |  | ☐
12 – Electronics | Cables | Crimp Ferrule Kit (covering sizes 24AWG to 18AWG) | 1 | Buy when needed | Ferrule kit |  |  | Research |  |  |  |  | ☐
12 – Electronics | Cables | MicroFit3 Connector Plug 4 Position | 4 | ⚡ Buy All Now | Toolhead/motor connectors — buy all |  |  | Research |  |  |  |  | ☐
12 – Electronics | Cables | MicroFit3 Connector Plug 3 Position | 1 | ⚡ Buy All Now | Toolhead/motor connectors — buy all |  |  | Research |  |  |  |  | ☐
12 – Electronics | Cables | MicroFit3 Connector Plug 2 Position | 2 | ⚡ Buy All Now | Toolhead/motor connectors — buy all |  |  | Research |  |  |  |  | ☐
12 – Electronics | Cables | MicroFit3 Connector Receptacle 4 Position | 4 | ⚡ Buy All Now | Toolhead/motor connectors — buy all |  |  | Research |  |  |  |  | ☐
12 – Electronics | Cables | MicroFit3 Connector Receptacle 3 Position | 1 | ⚡ Buy All Now | Toolhead/motor connectors — buy all |  |  | Research |  |  |  |  | ☐
12 – Electronics | Cables | MicroFit3 Connector Receptacle 2 Position | 2 | ⚡ Buy All Now | Toolhead/motor connectors — buy all |  |  | Research |  |  |  |  | ☐
12 – Electronics | Cables | MicroFit3 Female Pin | 40 | ⚡ Buy All Now | Connector pins — buy all |  |  | Research |  |  |  |  | ☐
12 – Electronics | Cables | MicroFit3 Male Pin | 40 | ⚡ Buy All Now | Connector pins — buy all |  |  | Research |  |  |  |  | ☐
12 – Electronics | Cables | WAGO 221-415 Lever-Nuts | 3 | ⚡ Buy All Now | Power distribution — buy all |  |  | Research |  |  |  |  | ☐
▶ 13 – BED ASSEMBLY — Buy these parts before this assembly step
13 – Bed Assembly | Fasteners | M4x6 BHCS | 7 | ⚡ Buy All Now | Bed mounting |  |  | Research |  |  |  |  | ☐
13 – Bed Assembly | Fasteners | M4 Knurled Nut (DIN 466-B) | 4 | ⚡ Buy All Now | Bed leveling thumbscrews |  |  | Research |  |  |  |  | ☐
13 – Bed Assembly | Electronics | Thermal Fuse (150C) | 1 | Buy when needed | Bed heater safety fuse |  |  | Research |  |  |  |  | ☐
13 – Bed Assembly | Misc | 3M VHB Tape 5952 | 1 | Buy when needed | Bed surface adhesive |  |  | Research |  |  |  |  | ☐
13 – Bed Assembly | Cables | MLX Power Receptacle 3 Position (bed wiring) | 1 | Buy when needed | Bed connector |  |  | Research |  |  |  |  | ☐
13 – Bed Assembly | Cables | MLX Power Plug 3 Position | 1 | Buy when needed | Bed connector |  |  | Research |  |  |  |  | ☐
13 – Bed Assembly | Cables | MLX Male Pin | 6 | ⚡ Buy All Now | Bed connector pins — buy all |  |  | Research |  |  |  |  | ☐
13 – Bed Assembly | Cables | MLX Female Pin | 6 | ⚡ Buy All Now | Bed connector pins — buy all |  |  | Research |  |  |  |  | ☐
13 – Bed Assembly | Buildplate | MIC6 5/16" Plate - 12"x12" | 1 | Buy when needed | Cast aluminum tooling plate bed |  |  | Research |  |  |  |  | ☐
13 – Bed Assembly | Buildplate | Adhesive Magnetic Sheet - 12"x12" | 1 | Buy when needed | Magnetic bed surface base |  |  | Research |  |  |  |  | ☐
13 – Bed Assembly | Buildplate | Spring Steel Flexible Print Surface - 12"x12" | 1 | Buy when needed | PEI flex plate |  |  | Research |  |  |  |  | ☐
13 – Bed Assembly | Buildplate | Keenovo Silicone AC Heater w/ thermistor - 250x250mm (450W) | 1 | Buy when needed | Bed heater |  |  | Research |  |  |  |  | ☐
▶ 14 – WIRING / FINAL — Buy these parts before this assembly step
14 – Wiring / Final | Cables | IGUS E2i-10-10-018-0 Chain (355mm [1.16ft]) | 2 | Buy when needed | Z drag chain |  |  | Research |  |  |  |  | ☐
14 – Wiring / Final | Cables | IGUS E2-100-10-12PZ Chain Ends (set) | 2 | ⚡ Buy All Now | Chain end sets — buy both |  |  | Research |  |  |  |  | ☐
14 – Wiring / Final | Cables | IGUS E2-15-10-028-0 Chain (495mm [1.62ft]) | 1 | Buy when needed | Toolhead drag chain |  |  | Research |  |  |  |  | ☐
14 – Wiring / Final | Cables | IGUS E2-150-10-12PZ Chain Ends (set) | 1 | ⚡ Buy All Now | Chain end sets — buy both |  |  | Research |  |  |  |  | ☐
ESTIMATED TOTAL (enter unit prices in col G) →

## Buy List by Step
Buy List by Step — What to Order Before Each Assembly Stage
▶ 1 – FRAME
Part | Qty | Buy All? | ☐ Ordered | ☐ Received
M5x40 SHCS | 22 | ⚡ Buy All
M5x30 BHCS | 22 | ⚡ Buy All
M5x16 BHCS | 35 | ⚡ Buy All
M5x10 BHCS | 35 | ⚡ Buy All
M5 Hexnut | 16 | ⚡ Buy All
M5 Post-install T-nut | 68 | ⚡ Buy All
M3 Post-install T-nut | 96 | ⚡ Buy All
M3 Hammer Head T-nuts | 60 | ⚡ Buy All
M3 Threaded Insert (M3x5x4) | 110 | ⚡ Buy All
Rubber Foot (1.5x.75", 38x19mm) | 4
OpenBuilds Billet Angle Corner Connector (2020) | 4
Misumi HFSB5-2020-290 | 1
Misumi HFSB5-2020-380 | 1
Misumi HFSB5-2020-400 | 2
Misumi HFSB5-2020-420-TPW | 10
Misumi HFSB5-2020-480-LCP-RCP | 4
Loctite Blue Threadlocker Stick | 1 | ⚡ Buy All
▶ 2 – Z DRIVE ASSEMBLY
Part | Qty | Buy All? | ☐ Ordered | ☐ Received
M3x40 SHCS | 30 | ⚡ Buy All
M3x30 SHCS | 25 | ⚡ Buy All
M3x20 SHCS | 22 | ⚡ Buy All
M3x16 SHCS | 20 | ⚡ Buy All
M3x8 SHCS | 180 | ⚡ Buy All
M3 Hexnut | 6 | ⚡ Buy All
M3 Washer | 4 | ⚡ Buy All
GT2 80T Pulley (5mm ID 6mm W) | 4
F695 Bearing | 20 | ⚡ Buy All
625 Bearing | 12 | ⚡ Buy All
GT2 Belt Loop (6mm W) - 188mm | 4
Linear Rail MGN9H 350mm | 6
NEMA17 Motor 17HS19-2004S | 6 | ⚡ Buy All
Mobil EP1/2 Grease | 1 | ⚡ Buy All
▶ 3 – AB DRIVE MODULES
Part | Qty | Buy All? | ☐ Ordered | ☐ Received
M5 1mm Shim | 42 | ⚡ Buy All
M3x25 SHCS | 6 | ⚡ Buy All
M3x12 SHCS | 41 | ⚡ Buy All
GT2 20T Pulley (5mm ID 6mm W) | 3
GT2 20T Pulley (5mm ID 9mm W) | 4
GT2 16T Pulley (5mm ID 6mm W) | 4
GT2 20T Toothed Idler (5mm ID 6mm W) | 2
GT2 20T Toothed Idler (5mm ID 9mm W) | 4
Ø5x60mm Shaft, D Cut | 4
Ø5x35mm Shaft (trim to size) | 1
GT2 Open Belt LL-2GT-6 (6mm wide) - 1800mm | 2
▶ 4 – GANTRY / XY JOINTS
Part | Qty | Buy All? | ☐ Ordered | ☐ Received
M3x10 FHCS | 4 | ⚡ Buy All
M3x6 FHCS | 8 | ⚡ Buy All
Linear Rail MGN12H 350mm | 1
Omron D2F-01L Micro Switch | 3
▶ 5 – TOOLHEAD
Part | Qty | Buy All? | ☐ Ordered | ☐ Received
BMG Extruder Components Kit | 1
Inductive Probe (See sourcing guide) | 1
Hotend Kit (24V) | 1
50x50x15 Centrifugal Fan (24V) | 1
40x40x10 Axial Fan (24V) | 1
NEMA14 Motor 36STH20-1004AHG | 1
4mm Threaded Bowden Coupler | 1
Ø6x3mm Neodimium Magnet | 8 | ⚡ Buy All
PTFE Tube (4mm OD 3mm ID) - 1000mm | 1
PTFE Tube (4mm OD 2mm ID) - 300mm | 1
▶ 6 – BELTING Z DRIVE
Part | Qty | Buy All? | ☐ Ordered | ☐ Received
GT2 Open Belt LL-2GT-9 (9mm wide) - 1100mm | 4
▶ 7 – LCD MODULE
Part | Qty | Buy All? | ☐ Ordered | ☐ Received
Mini 12864 Display | 1
▶ 8 – SKIRTS
Part | Qty | Buy All? | ☐ Ordered | ☐ Received
M3x6 BHCS | 11 | ⚡ Buy All
60x60x20 Fan (24V) | 3
▶ 9 – PANELS
Part | Qty | Buy All? | ☐ Ordered | ☐ Received
Single Sided Foam Tape 1mm Thick (5m) | 1
Single Sided Foam Tape 3mm Thick (5m) | 1
Coroplast Sheet - 419x419x4 mm | 2
Coroplast Sheet - 433x453x4 mm | 1
Acrylic Sheet Clear - 216.5x453x3 mm | 2
Acrylic Sheet Clear - 433x453x3 mm | 2
Acrylic Sheet Clear - 433x433x3 mm | 1
▶ 11 – EXHAUST FILTER
Part | Qty | Buy All? | ☐ Ordered | ☐ Received
Fume Extractor Carbon Filter Element | 1
▶ 12 – ELECTRONICS
Part | Qty | Buy All? | ☐ Ordered | ☐ Received
M3x50 SHCS | 2 | ⚡ Buy All
M2x10 Self-tapping Screw | 18 | ⚡ Buy All
ZF Rocker Switch DPST 16A ON-OFF | 1
TycoElectronics 10EGG1-1 Filtered Power Inlet (NA/UK) | 1
TycoElectronics 10EGG1-2 Filtered Power Inlet (EU) | 1
Medium Blow Fuse 5x20mm 4A (220V mains) | 2 | ⚡ Buy All
Medium Blow Fuse 5x20mm 8A (120v mains) | 1 | ⚡ Buy All
Keystone CAT6 Insert (Optional) | 1
Controller with 7+ Stepper outputs | 1
TMC2209 Stepper Motor Driver | 7 | ⚡ Buy All
USB Cable for selected controller | 1
RaspberryPi 3B+ or better | 1
Mean Well LRS-200-24 PSU | 1
Mean Well RS-25-5 PSU | 1
Omron G3A-210B-DC5 SSR | 1
DIN Rail Mount Bracket for G3A SSR | 1
BAT85 Diode | 1
C13 Power Cord | 1
DIN 3 Rails (35mm W) - 415mm | 2
Nylon Cable Ties, Small (.07-.10", 1.8-2.7mm wide) | 42 | ⚡ Buy All
18AWG Wire (10ft/3m total) | 1
20AWG High-flex Wire (10ft/3m total) | 1
22-24AWG High-flex Wire (min 19 strand)(250ft/76m total) | 1
Female Spade Crimp Terminal (18-22AWG, .250", 6.35mm) | 7 | ⚡ Buy All
Fork Spade Crimp Terminal (18-22AWG, #10) | 5 | ⚡ Buy All
Ring Crimp Terminal (16-22AWG, #6) | 1 | ⚡ Buy All
JST XH Connector, 3 Position Male/Female Pair plus Pins | 1 | ⚡ Buy All
Connector kit matching your controller choice (usually JST-XH) | 1
Crimp Ferrule Kit (covering sizes 24AWG to 18AWG) | 1
MicroFit3 Connector Plug 4 Position | 4 | ⚡ Buy All
MicroFit3 Connector Plug 3 Position | 1 | ⚡ Buy All
MicroFit3 Connector Plug 2 Position | 2 | ⚡ Buy All
MicroFit3 Connector Receptacle 4 Position | 4 | ⚡ Buy All
MicroFit3 Connector Receptacle 3 Position | 1 | ⚡ Buy All
MicroFit3 Connector Receptacle 2 Position | 2 | ⚡ Buy All
MicroFit3 Female Pin | 40 | ⚡ Buy All
MicroFit3 Male Pin | 40 | ⚡ Buy All
WAGO 221-415 Lever-Nuts | 3 | ⚡ Buy All
▶ 13 – BED ASSEMBLY
Part | Qty | Buy All? | ☐ Ordered | ☐ Received
M4x6 BHCS | 7 | ⚡ Buy All
M4 Knurled Nut (DIN 466-B) | 4 | ⚡ Buy All
Thermal Fuse (150C) | 1
3M VHB Tape 5952 | 1
MLX Power Receptacle 3 Position (bed wiring) | 1
MLX Power Plug 3 Position | 1
MLX Male Pin | 6 | ⚡ Buy All
MLX Female Pin | 6 | ⚡ Buy All
MIC6 5/16" Plate - 12"x12" | 1
Adhesive Magnetic Sheet - 12"x12" | 1
Spring Steel Flexible Print Surface - 12"x12" | 1
Keenovo Silicone AC Heater w/ thermistor - 250x250mm (450W) | 1
▶ 14 – WIRING / FINAL
Part | Qty | Buy All? | ☐ Ordered | ☐ Received
IGUS E2i-10-10-018-0 Chain (355mm [1.16ft]) | 2
IGUS E2-100-10-12PZ Chain Ends (set) | 2 | ⚡ Buy All
IGUS E2-15-10-028-0 Chain (495mm [1.62ft]) | 1
IGUS E2-150-10-12PZ Chain Ends (set) | 1 | ⚡ Buy All

## Key & Tips
Voron 2.4 JIT Purchase Tracker – Key & Tips
HOW TO USE
1. Parts are sorted by the assembly step that first needs them — this is your shopping trigger.
2. Before starting each assembly step, check what's listed under that heading and order/confirm receipt.
3. ⚡ YELLOW rows = 'Buy All Now' — these are consumables, fasteners, or parts needed at multiple stages. Buy the full BOM quantity the first time you need them.
4. White/blue rows = order just in time — single-use items that are only needed at one specific step.
5. Enter unit prices in column G; column H calculates the line total automatically.
6. Use the Buy List by Step sheet for a quick print-and-check shopping list format.
WHY 'BUY ALL NOW' FOR FASTENERS?
Fasteners like M3x8 SHCS (qty 180) are used in almost every subassembly. If you buy just what you need for step 2, you'll be placing 8 more orders. Buy the full BOM quantity once at the step that first needs them — same as buying all your lumber before a woodworking project.
The same applies to: bearings, T-nuts, heat-set inserts, connector pins, and other repeated small parts.
ORDER OF ASSEMBLY STEPS
1 – Frame Build the extrusion cube; install corner braces
2 – Z Drive Assembly Z motors, Z idlers, linear rails go in first
3 – AB Drive Modules A/B motor mounts, front idlers, gantry drives
4 – Gantry / XY Joints XY joints, gantry extrusions, Z belt clips
5 – Toolhead Extruder, hotend, probe — can print/assemble in parallel
6 – Belting Z Drive Route and tension Z belts
7 – LCD Module Mini 12864 display assembly
8 – Skirts Bottom skirts, exhaust fans, belt guards
9 – Panels Cut/order panels, install clips and doors
10 – Spool Holder Spool arm + Bowden retainer
11 – Exhaust Filter Carbon filter housing and grill
12 – Electronics PSUs, MCU, RPi, SSR, wiring harness
13 – Bed Assembly MIC6 plate, heater, PEI surface, Z endstop
14 – Wiring / Final Drag chains, final cable management